Dave Tate Day of Service

Bryan Park

Saturday, April 27 | 8:30-1, 80 volunteers

DAY OF CONTACTS

| Parks Staff: Floating: Kate Rivara; 804-350-3128 Michael Gee; 804-316-1529 Tree Planting: Qui Nguyen; 804-405-4543 Will Wickham; 804-551-1456 Front Entrance: Tiffany Concepcion; Until 1:30 804-405-9571 & Drew Lopez Southern Work Zone Boundary b/t Soccer and Market traffic : Ron Evans & E Sears; 804-218-8075 | Volunteer Group Andy Mason; arboristmason@gmail.com Phil Tate; Phil.tate@brightview.com Friends of Bryan Park Lunch: Rick Sinsabaugh, President; 804-517-6734 Randy Smith Trees: 804-833-4760 |
| --- | --- |

| FACILITATOR CONTACTS |  |  |
| --- | --- | --- |
| Tree Planting | Lunch | Tree Work |
| Randy Smith 804-833-4760 Qui, Will + Tree Stewards | Rick Sinsabaugh 804-517-6734 | Brightview: Phil Tate True Timber: Scott Turner Arborscapes: Billy Davis RW Stump: Reggie West Commonwealth Tree Care: Bartlett: Ethan Crockett Davey: Robert Holiday |
| Landscaping Entrance | Trash Pick up | Debris |
| Brightview | Self -Serve | Urban Forestry: Will Mayer +2 technicians & Brush Truck Park @ Keeper’s House |

Saturday, March 23 – SCHEDULE

Set-Up/Prep

6:00 am – staff to arrive at reporting location to head to Bryan

7:00 am – Install barricade @ front entrance – Stationed here: Tiffany & Drew

8:00 am – Install barricade & Station on Rosina’s Lane between parking lot and median – E Sears & Ron

7:45-8:15 – Volunteers and arborists arrive, park, walk to Shelter 1

Welcome & Orientation

8:30 – Welcome from Andy & Phil

Place Volunteers

9:00 am – Volunteers to Task Zones

Lunch

FoBP – 11:45 begin set up

Wrap-Up

12:30 – Scott Turner reflections

12:45 – Parks thank yous (Chris Frelke)

# SPECIAL INSTRUCTIONS:

- Parking:

  - Tree trucks to park directly in work zones.

  - UF truck at Keeper’s House.

  - ALL volunteers to park by Shelter 1.

  - Exceptions only for Tree Planting and Landscaping crews if they have materials to drop off. They must walk to and from Shelter 1 for kick-off/lunch.

  - Kabota can provide a ride for Randy Smith.

- Restrooms: Accessible porta potty at Shelter 1; Camphouse RR open for volunteers, Keeper’s House RR

- Rain Date: rain or shine. Cancelled in case of extreme weather.

- Medical: First aid kit at Shelter 1 and on Kabota. St Mary’s or MCV in case of emergency.

| Task |  |
| --- | --- |
| Tree work : Arborists will report to their work zones to remove dead and dangerous limbs |  |
| Brush hauling : Urban Forestry staff remove brush with claw truck | Park at Keeper’s House to wait for first pile. Follow behind tree work to stay out of active work zones. |
| Trash Pick up: Young volunteers and family members of crews | Self- Serve. Trash grabbers and bags will be available at Shelter 1 and Keeper’s House for walking crews. |
| Landscaping entrance Members of Brightview’s landscaping team will install new plantings at the stone gateway and apply fresh mulch. |  |
| Mulch mounding: Any chipped debris will be deposited for later spreading |  |
| Tree planting: - soaking tree diapers in water - filling tree holes with soil and amendments - packing down soil, while holding the tree upright - installing tree diapers at the base of trees - preparing protective wire tree cages for installation - installing tree cages using two 5' hardwood stakes & fastening zip ties - transport and distribute wood chips for protective mulch |  |
| Hopper Projects (tree team) - thinning the excess crowded trees (not pines, however), pruning invasives, dead branches, and vines from adjacent tree areas where mowing is not done - constructing tree cages for other trees in the Park - creating files of cleared brush & limbs for later removal |  |